## Actions
Good Soil action tracker
7 done / 7 not done |  | Experiential Corner budget: ₹1,20,000. Earlier target: 12–15 activities.
Status as of 13 Sep 2026. “Not done” means completion is not confirmed; update the dropdown as work is completed.
No. | Workstream | Action / expected outcome | Status | Next step / completion evidence
1 | Supplier outreach | Obtain a named Chitti sales executive’s direct phone number and email for institutional kit purchases. | Not done | Public support contact found: +91 98842 22368, support@chitti.app. A direct sales executive contact is still needed.
2 | Curriculum | Use Maheswari’s outline to align curriculum and kits for both batches, with 50% of topics following the same sequence. | Done | Completed: 25-class parallel curriculum aligned with 15-module robotics framework and Practiko multi-grade bundles in curriculum_plan.md.
3 | Group kits | Review the existing group kits and revise them where needed to match learning outcomes and batch suitability. | Done | Completed: 40 unique kit BOM (120 shared studio units + 600 take-home units) standardized on Practiko Mechatronics/Kinematics and Indian aeromodelling in BOM sheet.
4 | Curriculum catalogue | Create a curriculum catalogue in PDF or on the website, with kit descriptions, images and links to relevant site pages. | Done | Completed: Interactive web catalogue updated with 865 kits, search filters, and refactored curriculum preset in Vendor Research/index.html.
5 | Experiential research | Review the first Excel consolidating Instagram posts/pages and shortlist suitable experiential-corner kits. | Done | Completed: Consolidated Practiko multi-grade engineering suite (Mechatronics, Kinematics, Electrical, Hydraulics) analyzed and mapped.
6 | Experiential corner | Plan apparatus, kits and quantities for the Experiential Day Corner within ₹1,20,000, including an RC joystick simulator. | Not done | Use the relevant experiential flyer to confirm quantities. Earlier planning targets 12–15 activities. Prepare an itemised budget covering apparatus, kits, spares and delivery.
7 | Customer acquisition | Review AI e-commerce videos and build a customer-acquisition and sales pipeline for Good Soil. | Not done | Turn useful methods into a workflow from content/ads to enquiry capture, follow-up, purchase and repeat sales. Record the tools and measures for each stage.
8 | WhatsApp marketing | Set up WhatsApp marketing through the Meta/WhatsApp Business API for Good Soil’s online retail operation. | Not done | Combine both duplicate list entries into one workflow covering business setup, opt-ins, message templates, campaigns and sales follow-up.
9 | Mini-drone sourcing | Shortlist 2–3 mini-drone options and their vendors for purchase and educational use. | Not done | Compare delivered price, indoor suitability, controls, flight time, spare batteries, propeller guards and replacement-part availability.
10 | Teaching content | Create engaging lesson PPTs using suitable videos, games, infographics, animations and interactive quizzes. | Not done | Start with the aligned lesson sequence. Prepare one complete lesson deck and reusable slide structure, then develop the remaining lessons.
11 | Projection art | Evaluate “dil studio” and other suitable apps for projecting student drawings or 3D artwork onto a wall. | Not done | Confirm the app name, demonstrate the sketch-to-projection workflow, and record hardware needs, cost and a shareable sample projection.
12 | Aeromodelling research | Research Indian aeromodelling kit manufacturers, distributors and suppliers, including contacts and advertised prices. | Done | Completed: 13 supplier leads covering balsa, foam and RC kits. Price references checked 12 Sep 2026. See the supplier tab.
13 | Aeromodelling flyer | Create a supplier flyer summarising aeromodelling kits, pricing, contacts and bulk-order considerations. | Done | Completed: Aeromodelling_Suppliers_India_Flyer.pdf, a two-sided A4 flyer with all 13 supplier leads and clickable links.
14 | Aeromodelling selection | Obtain supplier quotes and select the right aeromodelling kits and prices for Good Soil’s EdTech programmes. | Done | Completed: Primary aeromodelling models selected (Crossvind balsa chuck gliders, Vortex-RC trainer, BrainHap mini-drones) and priced in BOM.

## Aeromodelling suppliers
Aeromodelling supplier reference
Advertised prices checked 12 Sep 2026. Not negotiated quotes. Confirm stock, GST, freight and exact kit contents.
Prices below span the named models/variants. Blank prices mean quotation required. Public contacts have not been contacted.
Supplier / location | Kit / material | Price from (₹) | Price to (₹) | MOQ (pieces) | Public business contact | Good Soil suitability / checks | Product source | Contact source
Crossvind Solutions — Kotdwar | All-balsa chuck kits: Little Pakshi (16 cm) ₹165; Tiny Tiya ₹310; Gnat Fighter ₹390; Crossbird (40 cm) ₹450. | 165 | 450 | On enquiry | +91 98114 75262 / +91 98101 99004 info@crossvindsolutions.com | First enquiry for low-cost balsa builds. Compare models at the same wingspan. Bulk discount and contents need a quote. | https://crossvindsolutions.com/chuck-glider-models/ | https://crossvindsolutions.com/
Indian Aero Fun — Delhi | Seagull balsa chuck-glider kit. | 450 | 450 | 10 | +91 80768 95235 / +91 99999 18706 info@indianaerofun.com | Published bulk listing. Reconfirm directory price, stock and exact kit specification. | https://www.exportersindia.com/product-detail/indian-aero-fun-chuck-glider-seagull-5644267.htm | https://www.indianaerofun.com/contact
Aero Model India / Hangar-S — Jodhpur | Seagull 35 cm kit with precut parts, drawing, instructions, sandpaper, glue and balancing clay. | 515 | 515 | On enquiry | +91 98294 91054 / +91 94141 27519 info@aeromodelindia.com | Useful larger balsa-kit benchmark. Listing showed 18 available. Confirm bulk quantity and institutional rates. | https://www.aeromodelindia.com/product/chuck-glider-seagull/ | https://www.aeromodelindia.com/contact/
New India Hobby Centre — Bengaluru | 40 cm balsa chuck-glider kit with building materials and instructions. |  |  | On enquiry | +91 98452 96906 / +91 98451 02103 newindiahobbycentre@gmail.com | Local workshop-kit and material lead. Price and wholesale terms not published. | https://www.newindiahobbycentre.com/aero.html | https://www.newindiahobbycentre.com/aero.html
AEROGO — Bengaluru | Free Style balsa ₹681.45; standard balsa ₹733.95; rubber-powered glider ₹838.95. | 681.45 | 838.95 | On enquiry | +91 70193 03830 contact@aerogo.live | Catalogue says tax-inclusive. Request kit-only pricing. Contact-page link returned unrelated content: confirm through phone/Instagram. | https://aerogo.live/ | https://www.instagram.com/aerogo.live/
Dhansamrat Toy Mart — Mumbai | 18.5-inch foam hand-launch airplane. Simple assembly-and-throw format. | 75 | 75 | 1 / 12: conflicting | +91 99875 57174 sales@dhansamrattoymart.com | Lowest public foam-plane price found. Confirm carton MOQ and exact foam type. India-based seller; manufacturing origin unverified. | https://www.tradeindia.com/products/foam-airplane-toy-c12134693.html | https://www.dhansamrattoymart.com/products
Mitsico — Surat | LED foam airplane, SKU SZ-1987. | 100 | 100 | 100 | 08047649165 (marketplace enquiry) Contact: Ronak Sheta | Simple foam activity. Duplicate listings differ in size/material; request exact SKU photos. WhatsApp not verified. | https://www.mitsico.in/kids-toys.html | https://www.mitsico.in/
Rozzby / CheaperZoneToys — Surat | Foam plane with lights; material field says thermocol. | 160 | 160 | 100 | 08047622002 (marketplace enquiry) Contact: Ghori Dhrumil | Confirm EPS/thermocol versus other foam. Dropshipping advertised. WhatsApp not verified. | https://www.cheaperzonetoys.com/plane.html | https://www.cheaperzonetoys.com/
Vortex-RC — Prayagraj | VT-Simple Trainer ₹1,650–₹3,399. F22 Raptor ₹1,799–₹4,149. Prices depend on kit variant. | 1650 | 4149 | Bulk enquiries: 6+ | +91 82994 71064 support@vortex-rc.com | Indian RC kit manufacturer. Bulk/dealership/co-branding policy dated 2016; reconfirm. Price airframe and complete electronics separately. | https://www.vortex-rc.com/product-category/rc-plane-kits/laser-cut-rc-airplane-kits-india/ | https://www.vortex-rc.com/bulk-orders-co-branding/
FlyingMachines RC Aviations — Thane | F22 Depron kit ₹1,800–₹4,500. Mig-29 Depron kit ₹2,200–₹5,000. | 1800 | 5000 | On enquiry | +91 86577 07173 support@flyingmachines.in | Both kits displayed sold out. Ask about production runs/restocking. Depron sheet 1000 × 650 × 5 mm listed at ₹320. | https://flyingmachines.in/ | https://flyingmachines.in/
Chitti / LMES Academy — Chennai | STEM programmes and aeromodelling workshops. Kit-only wholesale catalogue not verified. |  |  | Not published | +91 98842 22368 support@chitti.app | Public support contact only. Ask for a named sales executive, kit-only institutional supply and pricing. | https://chitti.app/ | https://chitti.app/support/
Alerios Aeroclub — Pune | Baka balsa/paper six-model kit, Spinboy rubber-powered balsa, EPP glider and 1 m balsa RC kit. |  |  | On enquiry | Official web contact form No public phone/email verified | Request kit-only quotes. Products differ: balsa-and-paper kit versus ready-to-fly EPP glider. | https://www.alerios.in/products | https://www.alerios.in/contact
Statica — Badlapur/Thane | Balsa/aeroply models on enquiry. Easy Chuck ₹199 and Seabird ₹249 are MDF. | 199 | 249 | On enquiry | +91 91520 15209 / +91 95943 35070 statica.sales@gmail.com | Listed price range is for MDF models only. Do not treat as a balsa price. Request a separate balsa/aeroply quotation. | https://statica.in/product/easy-chuck-glider/ | https://statica.in/contact/